## JNOWAV_1000
Lien #	Type	Comment	Assigned	Status	Reporter	Notes
1	AAREADME	AAREADME.TXT (& HTM) do not describe DATA/ directory contents.		Open	Vogt
2	AAREADME	File should list all of the directories on the volume and the nature of their content.		Open	Canu
3	AAREADME	It is recommend to remove these since 1) the standards don't allow for such / files at the top-level, and 2) all their info is in AAREADME.TXT		Open	Chen	Many people find these files useful, the data supplier strongly prefers to keep them.
4	Browse	BROWSE/…/*.LBL / Every file needs to be listed in a label, including the BROWSE .PNGs.	PWS	Resolved	Chen	Done
5	Catalog	.CAT file extension is not recognized on mac OS. [On Windows it's reserved for security catalog files.]		Open	Vogt	Add a note the AAREADME explaining that .CAT files are plain text and can be viewed with a text editor.
6	Catalog	There are a number of typos in the DATASET.CAT. (See original comments for list).		Open	Vogt
7	Catalog	Provide reference for note in DATASET.CAT stating that the density is “calculated from the equations of cold plasma theory”.		Open	Vogt	Barnhart et. al. reference added and paper itself included in the DOCUMENT directory
8	Catalog	DATASET.CAT still contains a number of "TO DO" lines.	PWS	Resolved	Canu / Vogt
9	Catalog	DATASET.CAT: / The diagnosis of the Fp from the continuum radiation cut-off assumes that this cut-off is local. Although non local cut-off is rather seldom, specifically taking into account the powerful continuum trapped in the Jovian magnetosphere, a sentence may be added regarding with this limitation, if the authors feel that this apply to their data sets.	PWS	Open	Canu
10	Catalog	DATASET.CAT: / In one of the provided documents, a sentence seems to indicate that if Fc > Fp, the diagnosis is not performed. I have not found such information in the DATASET.CAT. Is this relevant and missing or request clarification?	PWS	Open	Canu	Three different passes have been made through the dataset. The first by Ansher, only handled the case when Fce < Fpe. The second by Richards added upper hybrid frequency measurements and the third by Barnhart added cases where Fce > Fpe by looking at ordinary mode cutoffs.
11	Catalog	The papers referenced in the DATASET.CAT (Barbosa, Perraut, ….) should be listed in the REF.CAT.		Open	Canu	Done
12	Catalog	No format description included in the DATASET.CAT file.		Open	Canu	Done
13	Catalog	All are missing PDS_VERSION_ID = PDS3. Unfortunately, vtool complains if / those are there, but vtool is wrong there. / Recommend adding RECORD_TYPE = STREAM to all files.		Open	Chen	Done, PDS_VERSION_ID added to all label fragments
14	Catalog	CATALOG/DATASET.CAT / - LABEL_REVISION_NOTE is required (PDS Standards sec 5.3.1) but missing / - There is no space in the following values. / REFERENCE_KEY_ID = "GURNETTETAL 1992" / REFERENCE_KEY_ID = "BARNHARTETAL 2009" / REFERENCE_KEY_ID = "PERRAULTETAL 1998" / REFERENCE_KEY_ID = "BARBOSAETAL 1990B" / REFERENCE_KEY_ID = "SHAW&GURNETT 1980" / REFERENCE_KEY_ID = "MOSESETAL 1987" / should be / REFERENCE_KEY_ID = "GURNETTETAL1992" / ...		Open	Chen	Done
15	Catalog	CATALOG/INSTHOST.CAT / This is slightly obsolete, missing a Dec 2003 update by Steve Joy	PPI	Open	Chen	Done
16	Catalog	CATALOG/MISSION.CAT / This is slightly obsolete, missing a 2003-06 update by Steve Joy	PPI	Open	Chen	Done
17	Catalog	REF.CAT / Line 29 / REFERENCE_DESC = "B.L. Barnhart, W.S. Kurth, J.B. Groene, J.B. Faden, / should be / REFERENCE_DESC = "Barnhart, B.L., W.S. Kurth, J.B. Groene, J.B. Faden,		Open	Chen	Done
18	Data	yyyy-doyThh:mm:ss.000 difficult to work with in IDL.	PWS	Open	Canu / Vogt	Done: PWS team generated the data files using / yyyy-mm-dd… times
19	Data	Some software has trouble reading the empty data values, represented by two commas ("…,,…"). Flag or fill values would be easier to work with. (See list of specific problem files in Vogt's comments).		Open	Khurana / Vogt	This is a standard convention for CSV files. No change will be made to the data files, but it may be useful to make sure that this is documented.
20	Data	It would be useful to have spacecraft jovigraphic latitude and local time provided in addition to the spacecraft position parameters already provided.	PWS	Open	Vogt	Done file format changed and new values added using spice in combination with local calculations
21	Data	The SCET in ASCII is not in ISO form, since the date is provided with Day of Year rather than Day/MONTH, hence most standard routines reading ASCII time or converting it (ie READ_CSV in IDL) are not able to manipulate time directly, which can be troublesome for basic users.	PWS	Open	Canu	Done, changed to YYYY-MM-DD format.
22	Data	Some files have all density values set to '0.00', while the frequency has a value and the quality flag get values from 0 to 2. This is the case for all files in the Jupiter0 directory, and can be confirmed by the empty density plot in the browse files.	PWS	Open	Canu	Done, all 553 days of data were checked for reasonable data, review by a scientist is the field is still pending
23	Data	Some files have very low frequencies (below 100 Hz) and hence density values (10-6/cc), ie in Ganymede7 (1997/04/01). Is it realistic? / This case corresponds to Fp << Fc, which was said to be disregarded in the provided documents (thesis)	PWS	Open	Canu	Done, reference to Barnhart's work adding Fp << Fc measurements to the volume included. Barnhart's paper was also added to the volume.
24	Document	DOCUMENT/A_D79_358_1.PNG, DOCUMENT/RICHARDS_2006.PDF / These files must be listed in a label(s).		Open	Chen	Done
25	Document	Line 9: / INSTRUMENT_NAME = "PLASMA WAVES SUBSYSTEM" / should match what CATALOG/PWS_INST.CAT has, i.e. / INSTRUMENT_NAME = "PLASMA WAVE RECEIVER" / Line 24: DOCUMENT_FORMAT = "PDF" should be "ADOBE PDF" / Line 32: extra, incorrect END_OBJECT = FILE / Lines 39, 52, 71: no such file IMAGE_01.PNG, IMAGE_02.PNG, IMAGE_03.PNG / ^DOCUMENT = "IMAGE_01.PNG"		Open	Chen	Done, DOCUMENT.LBL has been re-written
26	Document	DOCUMENT/DOCUMENTS.LBL / This file is incomplete		Open	Chen	Done
27	ERRATA	First line is (no P) / DS_VERSION_ID = PDS3	PWS	Resolved	Chen
28	Index	INDEX/INDEX.LBL / - I recommend adding / RECORD_TYPE = STREAM / - Line 9: / INSTRUMENT_NAME = "PLASMA WAVE SUBSYSTEM" / should be / INSTRUMENT_NAME = "PLASMA WAVE RECEIVER" / - Field VOLUME_ID is required. If constant, it can be a keyword, i.e. / VOLUME_ID = GOPW_2001		Open	Chen	Done, but note that Bill wants the name to be / 'Plasma Wave Science'
29	Label	Data file labels: / It is possible to infer the meaning of the elements of the spacecraft event time, but it would be useful have them specifically identified in the field description.		Open	Vogt	Done, SCET field description has been expanded
30	Label	There is not mention of the specific DOY choice, which is not reflected by the Start and Stop time in the label, which are them in ISO format.	PWS	Open	Canu	Lien may be closed if time format is changed to YYYY-MM-DD
31	Label	All labels have / TARGET_NAME = "JUPITER" / Would it make sense to add or change that to GANYMEDE, CALLISTO, ...?	PWS	Open	Chen	Done
32	PDS DD	EN must add the following values to the data dictionary: / MISSION_PHASE_NAME: / "EUROPA 11 ORBIT", / "EUROPA CAMPAIGN", / "GALILEO-CASSINI", / "INNER JUPITER", / "IO CAMPAIGN (GMM)", / "IO CAMPAIGN", / "PERIJOVE REDUCTION CAMPAIGN", / "EUROPA 11 ENCOUNTER",	PDS EN	Open	Chen
33	Text Files	The following files contains lines which do not have CRLF line terminators: AAREADME.LBL, AAREADME.TXT, ERRATA.TXT, */*INFO.TXT, DOCUMENT/ANSHER_2001.LBL,	PWS	Resolved	Chen